## Overview
RAG2ATT&CK — Replication-and-Extension Study Project Tracker
Project / repository name | RAG2ATTCK
Teacher-assigned topic | Trợ lý AI phân loại và ánh xạ kỹ thuật tấn công theo khung MITRE ATT&CK từ log hệ thống. |  | Status | Count
Final research topic | Evaluating MITRE ATT&CK-Grounded RAG for Technique Attribution from Windows Endpoint Logs: A Replication-and-Extension Study. |  | Not Started | 32
Research nature | Controlled empirical replication + extension; not a new RAG algorithm. |  | In Progress | 1
Replication component | Same LLM + same Windows endpoint samples: No-RAG vs ATT&CK-grounded RAG. |  | Blocked | 0
Extension component | Exact Technique/Sub-technique attribution + retrieval-success / LLM-failure decomposition. |  | Done | 3
Dataset scope | 8–10 techniques/sub-techniques; ~400–500 evaluation samples after leakage audit.
Scope guardrail | No fine-tuning, agent, Wazuh/SIEM integration, dashboard, knowledge graph, or custom SDK. |  | KPI | Value
|  |  | Total tasks | 36
|  |  | Completed tasks | 3
|  |  | Overall progress | 9.306%
Three Research Questions
RQ1 | How does MITRE ATT&CK-grounded RAG affect exact technique/sub-technique attribution accuracy from Windows endpoint logs compared with the same LLM without retrieval? | Role | Replication | Metrics | Accuracy / Macro-F1
RQ2 | How does retrieval success/quality affect end-to-end ATT&CK technique attribution accuracy? | Role | Main extension | Metrics | Recall@k + conditional accuracy + failure decomposition
RQ3 | How does retrieval depth k affect accuracy, latency, and token usage? | Role | Ablation | Conditions | k = 1 / 3 / 5 / 10

## Roadmap
8-Week Roadmap — Replication-and-Extension Study
Phase | Week | Date Range | Task ID | Task | Objective / Acceptance Criteria | Owner | Priority | Dependency | Deliverable | Status | Progress %
Literature & Scope | W1 | 15–21 Sep 2026 | T01 | Freeze teacher-topic → research-topic framing | Final title states replication-and-extension; preserves teacher-assigned System Logs + AI + MITRE ATT&CK scope; no novelty overclaim. | Shared | Critical | — | Approved framing statement | Done | 100%
Literature & Scope | W1 | 15–21 Sep 2026 | T02 | Read/annotate closest comparator papers | Read Yang & Hsu, AWS-RAG, Trace2ATT&CK, TechniqueRAG/H-TechniqueRAG, LADE, CAM-LDS and Okuma sufficiently to defend similarities/differences. | User | High | T01 | Annotated reading notes | In Progress | 35%
Literature & Scope | W1 | 15–21 Sep 2026 | T03 | Finalize 3 RQs and hypotheses | RQ1 replication; RQ2 main diagnostic extension; RQ3 Top-k ablation. Metrics mapped to each RQ. | Shared | Critical | T01 | RQ/Hypothesis matrix | Done | 100%
Literature & Scope | W1 | 15–21 Sep 2026 | T04 | Finalize comparator/gap matrix | Comparator/gap matrix from the completed literature screening is frozen; user deep-reading/annotation continues separately under T02. | AI | High | T01 | Related Work Matrix | Done | 100%
Data & Ground Truth | W2 | 22–28 Sep 2026 | T05 | Acquire public Windows ATT&CK-labeled dataset | Dataset accessible locally; source/version/license recorded. Candidate: Windows-APT 2025 or equivalent after schema verification. | Shared | Critical | T03 | Dataset snapshot + source record | Not Started | 0%
Data & Ground Truth | W2 | 22–28 Sep 2026 | T06 | Profile labels and evidence fields | Count Technique/Sub-technique labels; inspect raw evidence and identify answer-bearing/rule-derived fields. | AI | Critical | T05 | Schema + class distribution report | Not Started | 0%
Data & Ground Truth | W2 | 22–28 Sep 2026 | T07 | Freeze 8–10 technique/sub-technique subset | Selected labels have enough samples, defensible endpoint evidence, and manageable balance. | User | Critical | T06 | Final label list | Not Started | 0%
Data & Ground Truth | W2 | 22–28 Sep 2026 | T08 | Build sanitizer / strict field whitelist | No ATT&CK label/tactic/rule.mitre/answer-bearing description reaches model or retriever query. | AI | Critical | T05;T06 | sanitizer.py + tests | Not Started | 0%
Data & Ground Truth | W2 | 22–28 Sep 2026 | T09 | Run leakage audit + manual spot-check | Automated scan and manual review pass; findings documented. | Shared | Critical | T08 | Leakage audit log | Not Started | 0%
Data & Ground Truth | W2 | 22–28 Sep 2026 | T10 | Create balanced evaluation subset | ~40–50 samples/class; exact sample IDs + seed stored; ground truth separated from model input. | AI | High | T07;T09 | processed evaluation file | Not Started | 0%
No-RAG Baseline | W3 | 29 Sep–5 Oct 2026 | T11 | Choose and pin one LLM/API | One provider/model/version for all conditions; settings and API access documented. | User | Critical | T03 | Model config | Not Started | 0%
No-RAG Baseline | W3 | 29 Sep–5 Oct 2026 | T12 | Implement unified LLM client + output schema | Stable JSON technique_id output; retry/errors/tokens/latency logged. | AI | High | T11 | llm_client.py | Not Started | 0%
No-RAG Baseline | W3 | 29 Sep–5 Oct 2026 | T13 | Freeze baseline/base prompt | Versioned prompt requests exact Technique/Sub-technique ID; frozen before main run. | Shared | High | T12 | prompt_v1 | Not Started | 0%
No-RAG Baseline | W3 | 29 Sep–5 Oct 2026 | T14 | Smoke-test synthetic Sysmon-style logs | 20–30 synthetic cases validate parser/API/output/evaluator only; not used as research evidence. | Shared | Medium | T12;T13 | Smoke-test results | Not Started | 0%
No-RAG Baseline | W3 | 29 Sep–5 Oct 2026 | T15 | Run small real-data No-RAG pilot | 20–50 sanitized real samples; inspect schema failures, mappings, cost and latency. | User | High | T10;T13 | Pilot predictions | Not Started | 0%
RAG Pipeline | W4 | 6–12 Oct 2026 | T16 | Pin ATT&CK Enterprise release / STIX | Exact release/date/source recorded; same release used for retrieval and ID validation. | Shared | Critical | T03 | ATT&CK snapshot | Not Started | 0%
RAG Pipeline | W4 | 6–12 Oct 2026 | T17 | Build Windows ATT&CK technique corpus | Fixed document fields such as technique_id/name/description/platforms; corpus definition frozen. | AI | High | T16 | ATT&CK corpus JSON | Not Started | 0%
RAG Pipeline | W4 | 6–12 Oct 2026 | T18 | Build embedding + FAISS index | Local index returns ranked ATT&CK candidates reproducibly. | AI | High | T17 | FAISS index | Not Started | 0%
RAG Pipeline | W4 | 6–12 Oct 2026 | T19 | Implement RAG branch with retrieved context | Same base prompt/model/schema; only ATT&CK retrieved context differs. | AI | Critical | T18;T13 | rag_pipeline.py | Not Started | 0%
RAG Pipeline | W4 | 6–12 Oct 2026 | T20 | Implement retrieval diagnostics | Record ranks and whether ground truth appears in Top-1/3/5/10; compute Recall@k. | Shared | Critical | T18;T10 | Retriever diagnostics report | Not Started | 0%
Main Experiments | W5 | 13–19 Oct 2026 | T21 | Freeze experimental protocol | Dataset IDs, model/version, prompts, ATT&CK release, embedding model, k, seed, retry/logging locked. | User | Critical | T15;T20 | experiment_config.yaml/json | Not Started | 0%
Main Experiments | W5 | 13–19 Oct 2026 | T22 | Run No-RAG full evaluation | Cache raw response, parsed prediction, tokens, latency and error status for each sample. | User | Critical | T21 | no_rag_predictions.jsonl | Not Started | 0%
Main Experiments | W5 | 13–19 Oct 2026 | T23 | Run RAG k=1 | Log retrieved candidate/rank, final prediction, tokens and latency. | User | High | T21 | rag_k1_predictions.jsonl | Not Started | 0%
Main Experiments | W5 | 13–19 Oct 2026 | T24 | Run RAG k=3 | Same settings; log candidates/ranks and final prediction. | User | High | T21 | rag_k3_predictions.jsonl | Not Started | 0%
Main Experiments | W5 | 13–19 Oct 2026 | T25 | Run RAG k=5 | Primary mid-range condition; complete retrieval + generation logs. | User | Critical | T21 | rag_k5_predictions.jsonl | Not Started | 0%
Main Experiments | W5 | 13–19 Oct 2026 | T26 | Run RAG k=10 | High-context condition for coverage vs noise/cost analysis. | User | Medium | T21 | rag_k10_predictions.jsonl | Not Started | 0%
Evaluation | W6 | 20–26 Oct 2026 | T27 | Compute end-to-end mapping metrics | Exact Accuracy, Macro-F1, per-class P/R, invalid-ID rate for every condition. | AI | Critical | T22:T26 | Metrics tables | Not Started | 0%
Evaluation | W6 | 20–26 Oct 2026 | T28 | Compute retrieval metrics + conditional accuracy | Recall@1/3/5/10 and final accuracy conditioned on GT present/absent in retrieved set. | AI | Critical | T23:T26 | Retrieval/conditional metrics | Not Started | 0%
Evaluation | W6 | 20–26 Oct 2026 | T29 | Decompose RAG failures | Separate retrieval failure, LLM selection/generation failure, invalid IDs, ambiguous-evidence cases. | Shared | Critical | T27;T28 | Error-analysis table | Not Started | 0%
Evaluation | W6 | 20–26 Oct 2026 | T30 | Answer RQ1–RQ3 | RQ1 replication conclusion; RQ2 failure mechanism; RQ3 accuracy/cost trade-off. | Shared | Critical | T27:T29 | RQ answer summary | Not Started | 0%
Report | W7 | 27 Oct–2 Nov 2026 | T31 | Write Methodology | Explain teacher topic → narrowed scope; replication/extension; dataset/leakage; retrieval; controls; metrics. | Shared | High | T30 | Methods draft | Not Started | 0%
Report | W7 | 27 Oct–2 Nov 2026 | T32 | Write Results & Discussion | Report whether replication succeeds/fails; explain retrieval vs LLM bottlenecks; no unsupported generalization. | Shared | Critical | T30 | Results/Discussion draft | Not Started | 0%
Report | W7 | 27 Oct–2 Nov 2026 | T33 | Finalize Related Work / gap wording | Do not claim RAG, Top-k, Sysmon-RAG or retrieval analysis is globally novel; position setting-specific extension. | Shared | Critical | T02;T04 | Related Work section | Not Started | 0%
QA & Submission | W8 | 3–9 Nov 2026 | T34 | Reproducibility QA | Fresh subset run reproduces pipeline; versions/configs/sample IDs/results traceable. | User | High | T31:T33 | QA checklist | Not Started | 0%
QA & Submission | W8 | 3–9 Nov 2026 | T35 | Prepare presentation/demo | Teacher topic → literature → replication gap → design → RQs → results → limitations. | Shared | High | T32;T33 | Presentation | Not Started | 0%
QA & Submission | W8 | 3–9 Nov 2026 | T36 | Final submission package | Report, code, configs, prompts, references, results and allowed raw outputs reviewed. | User | Critical | T34;T35 | Submission package | Not Started | 0%

## RQ_Experiments
Replication-and-Extension Research Questions → Experimental Design
RQ | Research Question | Hypothesis | Independent Variable | Dependent Variable | Conditions | Metrics | Required Output | Decision Rule
RQ1 | How does MITRE ATT&CK-grounded RAG affect exact ATT&CK technique/sub-technique attribution accuracy from Windows endpoint logs compared with the same LLM without retrieval? | H1: Macro-F1(RAG) > Macro-F1(No-RAG) | RAG condition | Exact mapping quality | No-RAG; RAG k=1/3/5/10 | Accuracy; Macro-F1; per-class P/R; invalid-ID rate | Controlled comparison + per-class errors | Replication may confirm, weaken or contradict prior RAG gains.
RQ2 | How does retrieval success/quality affect end-to-end ATT&CK technique attribution accuracy? | H2: Final correctness is higher when ground-truth technique is present in retrieved Top-k | GT present in Top-k / retrieval rank | Final prediction correctness | RAG k=1/3/5/10 | Recall@k; conditional accuracy; retrieval-failure vs LLM-failure counts | Retrieval→generation decomposition | Main extension: diagnose where RAG fails in Windows endpoint setting.
RQ3 | How does retrieval depth k affect accuracy, latency, and token usage? | H3: Intermediate k may give best accuracy-cost trade-off | Retrieval depth k | Accuracy + tokens + latency | k=1,3,5,10 | Macro-F1; Accuracy; tokens; latency | Top-k ablation table/plot | Ablation/diagnostic, not an independent novelty claim.

## Resources
Resources, Prior Work & Reuse Plan — Latest Framing
Category | Resource | Role | Reuse / Build | User Action | Priority | Source / DOI | Notes
Knowledge | MITRE ATT&CK Enterprise STIX/JSON | Fixed RAG corpus + ID validation | Reuse | Pin one release before experiment | Critical | https://attack.mitre.org/ | RAG corpus is not manually authored.
Dataset | Windows-APT 2025 or verified equivalent | Windows endpoint ground truth | Reuse | Verify schema/license/label leakage | Critical | https://doi.org/10.1016/j.dib.2026.112569 | Candidate; final choice follows field-level audit.
Model | One LLM provider/API | Same model for all conditions | Reuse | Choose/pin provider/model/version/parameters | Critical | Provider documentation | Do not benchmark multiple LLMs in main study.
Retrieval | Embedding model + FAISS | Top-k ATT&CK retrieval | Reuse | Pin embedding model/version | High | https://github.com/facebookresearch/faiss | Top-k is retrieval depth, not LLM sampling top_k.
Evaluation | scikit-learn + evaluator | Accuracy/Macro-F1/P/R | Reuse + Build | None beyond environment | High | https://scikit-learn.org/ | Store raw predictions for traceability.
Prior work | Yang & Hsu (2026) | Closest system/input comparator | Read/Cite | Read carefully | Critical | https://doi.org/10.1007/978-3-032-24063-7_18 | Windows Sysmon + RAG; malicious behavior detection focus.
Prior work | AWS CloudTrail RAG (2026) | Closest experimental-design comparator | Read/Cite | Read carefully | Critical | https://doi.org/10.32604/cmc.2026.077606 | Controlled RAG-vs-baseline ATT&CK mapping on cloud telemetry.
Prior work | Trace2ATT&CK (2026) | Telemetry + ATT&CK-grounded RAG | Read/Cite | Read method/evaluation | High | https://arxiv.org/abs/2609.12841 | Linux/eBPF provenance-graph setting.
Prior work | TechniqueRAG (2025) | ATT&CK RAG + retrieval/reranking | Read/Cite | Use to avoid false novelty | High | https://doi.org/10.18653/v1/2025.findings-acl.1076 | CTI text; retrieval analysis already exists.
Prior work | H-TechniqueRAG (2026) | Hierarchical ATT&CK RAG + Top-k/context analysis | Read/Cite | Bound RQ3 novelty | High | https://arxiv.org/abs/2604.14166 | CTI text, not endpoint telemetry.
Prior work | CAM-LDS (2026) | Exact technique mapping + leakage/evaluation lessons | Read/Cite | Read methods/evaluation | Critical | https://doi.org/10.1007/s10207-026-01318-x | Important anti-label-leakage comparator.
Prior work | Okuma et al. (2023) | Windows Sysmon → ATT&CK foundation | Read/Cite | Historical foundation | High | https://doi.org/10.1109/ICSPIS60075.2023.10343783 | Windows log-to-technique mapping is not novel itself.
Review | Systematic Review (2026) | TTP extraction landscape | Read/Cite | Related-work framing | High | https://arxiv.org/abs/2604.02377 | Useful synthesis; not sole evidence.
Project code | Loader + sanitizer + ATT&CK loader + retriever + LLM client + evaluator | Research prototype | Build | Run/validate; keep configs/results | Critical | Project repository | No custom SDK/agent/SIEM/dashboard/KG required.
Prior work | LADE (2026) | Host-side command/script behavior → ranked ATT&CK techniques | Read/Cite | Use to bound host-telemetry / Top-k novelty | High | https://doi.org/10.1007/978-3-032-32767-3_11 | Top-3/Top-10 style evaluation; not the same controlled Windows RAG-vs-No-RAG task.
Positioning | Primary replication anchor: AWS CloudTrail RAG (2026) | Conceptual replication of treatment contrast | Use | Replicate No-RAG vs ATT&CK-grounded RAG, not the exact original protocol | Critical | https://doi.org/10.32604/cmc.2026.077606 | Closest experimental-design work; CloudTrail telemetry differs from Windows endpoint telemetry.
Positioning | Primary system comparator: Yang & Hsu (2026) | Closest Windows Sysmon + RAG architecture | Use | Different target: malicious-behavior detection vs exact ATT&CK Technique/Sub-technique attribution | Critical | https://doi.org/10.1007/978-3-032-24063-7_18 | Nearest system-level work; not the same research output task.
Guardrail | Canonical contribution statement | Research positioning | Use | Keep in proposal/report/agent handoff | Critical | Project decision | Novelty/value is not Windows, RAG, ATT&CK, or Top-k individually; it is the controlled conceptual replication in a Windows exact-technique setting plus retrieval-vs-LLM failure decomposition.
Handoff | Source-of-truth rule | Context continuity | Use | Sheet = project status; Doc = methodology/gap; Doc Section 14 overrides stale framing | High | Google Drive context package | If task status differs, follow the Sheet; if methodological framing differs, follow Doc Section 14.